## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Requirement Analysis | MUST HAVE | No Dependency | All team members | 3- Completed
S1 | S1 | US-002 | Finalize Technology Stack (React, Node, MongoDB, APIs) | MUST HAVE | Research & Tech Evaluation | All team members | 3- Completed
S1 | S1 | US-003 | System Architecture Design | MUST HAVE | Architecture Planning | Bhavana , Yash , Akhil | 3- Completed
S2 | S1 | US-004 | GitHub Repository & Project Structure Setup | MUST HAVE | GitHub | All team members | 3- Completed
S2 | S1 | US-005 | JWT Authentication Implementation | MUST HAVE | Backend Setup | Yash Raj , Akhil , Parth | 3- Completed
S2 | S2 | US-006 | MongoDB Configuration | MUST HAVE | Database Setup | Parth , Isha , Shivani | 3- Completed
S3 | S2 | US-007 | AbuseIPDB API Integration | MUST HAVE | API Key | Yash , Shrividya , isha | 3- Completed
S3 | S2 | US-008 | AlienVault OTX Integration | MUST HAVE | API Key | Bhavana , Shivani , shreya | 3- Completed
S4 | S2 | US-009 | Threat Simulation Engine Development | MUST HAVE | Backend Logic | Bhavana , Shreya , Shivani | 3- Completed
S4 | S2 | US-010 | Socket.IO Real-time Broadcasting | MUST HAVE | Node.js Setup | Akhil , Shivani , Parth | 3- Completed
S5 | S3 | US-011 | Global Threat Map Implementation | MUST HAVE | Geo Mapping API | Yash , Shrividya , Shivani | 3- Completed
S5 | S3 | US-012 | Dashboard Visualizations Development | MUST HAVE | Chart Libraries | Isha , Bhavana , Shreya | 3- Completed
S6 | S3 | US-013 | MITRE ATT&CK Mapping Integration | MUST HAVE | MITRE Framework Reference | Parth , Shreya , Aditi | 3- Completed
S6 | S3 | US-014 | Nmap Scan Module Development | MUST HAVE | Nmap Tool | Aditi , Shivani , Isha | 3- Completed
S6 | S4 | US-015 | IP Reputation Module | MUST HAVE | Threat Intelligence APIs | Akhil, Yash , Aditi | 3- Completed
S7 | S4 | US-016 | QR / URL Scanner Implementation | MUST HAVE | URL Analysis Logic | Yash , Bhavana , Isha | 3- Completed
S7 | S4 | US-017 | AI Assistant Integration | MUST HAVE | LLM API | Bhavana , shreya | 3- Completed
S7 | S4 | US-018 | RAG Knowledge System Implementation | MUST HAVE | Vector Database | Shrividya, Parth , Aditi | 3- Completed
S8 | S4 | US-019 | Dockerization of Application | MUST HAVE | Docker | Shivani , Parth , Shivani | 3- Completed
S8 | S5 | US-020 | Nginx Configuration | MUST HAVE | Server Setup | Isha , Shivani , Parth , Yash | 3- Completed
S8 | S5 | US-021 | Role-Based Dashboard Implementation | MUST HAVE | Authentication System | Aditi , Akhil , Shrividya | 3- Completed
S9 | S5 | US-022 | Data Optimization & Performance Tuning | MUST HAVE | Backend Optimization | Yash , Bhavana , Isha | 3- Completed
S9 | S5 | US-023 | System Testing & Bug Fixing | MUST HAVE | Complete System | Aditi , Shivani , Shrividya | 3- Completed
S9 | S5 | US-024 | Agile Documentation Preparation | MUST HAVE | Sprint Records | Yash , Shreya , Aditi | 3- Completed
Completed Work (Re-Structured & Updated)
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | Sprint 1 | US-001 | Project Requirement Analysis | MUST HAVE | No Dependency | bhavana, rahul, priya | 3 - Completed
S1 | Sprint 1 | US-002 | Finalize Technology Stack | MUST HAVE | Project Architecture Diagram | rajesh, naveen, malini | 3 - Completed
S2 | Sprint 1 | US-003 | System Architecture Design | MUST HAVE | Project Architecture Diagram | sandeep, oneeka, irfana | 3 - Completed
S2 | Sprint 1 | US-004 | GitHub & Project Structure Setup | MUST HAVE | GitHub Repository Setup | priya, rajesh, oneeka | 3 - Completed
S3 | Sprint 2 | US-005 | JWT Authentication | MUST HAVE | Node.js & Express Setup | rahul, rajesh, naveen | 3 - Completed
S3 | Sprint 2 | US-006 | MongoDB Configuration | MUST HAVE | MongoDB Atlas Configuration | rajesh, naveen, priya | 3 - Completed
S4 | Sprint 2 | US-007 | AbuseIPDB API Integration | MUST HAVE | AbuseIPDB API Key | sandeep, rahul, irfana | 3 - Completed
S4 | Sprint 2 | US-008 | AlienVault OTX Integration | MUST HAVE | AlienVault OTX API Key | malini, oneeka, sandeep | 3 - Completed
S5 | Sprint 3 | US-009 | Threat Simulation Engine | MUST HAVE | AbuseIPDB Blacklist Data | rahul, naveen, sandeep | 3 - Completed
S5 | Sprint 3 | US-010 | Socket.IO Broadcasting | MUST HAVE | Socket.IO Setup | oneeka, malini, rajesh | 3 - Completed
S6 | Sprint 3 | US-011 | Global Threat Map | MUST HAVE | Mapbox | oneeka, malini, irfana | 3 - Completed
S6 | Sprint 3 | US-012 | Dashboard Visualizations | MUST HAVE | Recharts Library | naveen, rahul, priya | 3 - Completed
S7 | Sprint 4 | US-013 | MITRE ATT&CK Mapping | SHOULD HAVE | MITRE ATT&CK Dataset Mapping | irfana, rajesh, rahul | 3 - Completed
S7 | Sprint 4 | US-014 | Nmap Scan Module | MUST HAVE | Nmap Installation | irfana, naveen, sandeep | 3 - Completed
S8 | Sprint 4 | US-015 | IP Reputation Module | MUST HAVE | AbuseIPDB API | malini, oneeka, priya | 3 - Completed
S8 | Sprint 4 | US-016 | QR / URL Scanner | SHOULD HAVE | AlienVault OTX API | bhavana, rahul, rajesh | 3 - Completed
S9 | Sprint 5 | US-017 | AI Assistant | MUST HAVE | Gemini / OpenRouter API Key | naveen, rahul, bhavana | 3 - Completed
S9 | Sprint 5 | US-018 | RAG Knowledge System | SHOULD HAVE | knowledge.json (RAG Dataset) | naveen, rajesh, priya | 3 - Completed
S10 | Sprint 5 | US-019 | Dockerization | MUST HAVE | Docker Setup | priya, sandeep, rajesh | 3 - Completed
S10 | Sprint 5 | US-020 | Nginx Configuration | SHOULD HAVE | Nginx Reverse Proxy | sandeep, naveen, oneeka | 3 - Completed
S11 | Sprint 5 | US-021 | Role-Based Dashboard | MUST HAVE | JWT Authentication | oneeka, malini, rahul | 3 - Completed
S11 | Sprint 5 | US-022 | Data Optimization | SHOULD HAVE | MongoDB Optimization Queries | rajesh, naveen, priya | 3 - Completed
S12 | Sprint 5 | US-023 | System Testing | MUST HAVE | Integrated Module Testing | rahul, oneeka, irfana | 3 - Completed
S12 | Sprint 5 | US-024 | Agile Documentation | MUST HAVE | Project Documentation | bhavana, malini, priya | 3 - Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 229 | 68 | 42 | 37 | 30 | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1 | Project Requirement Analysis | 2026-01-05 | 2026-01-06 | Yash Raj , Bhavana , Shreya | Planning | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Finalize Technology Stack | 2026-01-06 | 2026-01-07 | Isha , Shivani , Parth , Yash | Planning | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | System Architecture Design | 2026-01-07 | 2026-01-08 | Bhavana , Yash , Akhil | Planning | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | GitHub & Project Structure Setup | 2026-01-09 | 2026-01-10 | Bhavana , Isha , Parth | Setup | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | JWT Authentication | 2026-01-13 | 2026-01-14 | Yash Raj , Akhil , Parth | Setup | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 6 | MongoDB Configuration | 2026-01-15 | 2026-01-16 | Parth , Isha , Shivani | Setup | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 7 | AbuseIPDB API Integration | 2026-01-16 | 2026-01-17 | Yash , Shrividya , isha | Setup | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 8 | AlienVault OTX Integration | 2026-01-18 | 2026-01-19 | Bhavana , Shivani , shreya | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 9 | Threat Simulation Engine | 2026-01-21 | 2026-01-22 | Bhavana , shreya , shivani | Coding | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 10 | Socket.IO Broadcasting | 2026-01-23 | 2026-01-24 | Akhil , Shivani , Parth | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 11 | Global Threat Map | 2026-01-24 | 2026-01-25 | Yash , Shrividya , Shivani | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 12 | Dashboard Visualizations | 2026-01-26 | 2026-01-27 | Isha , Bhavana , Shreya | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 13 | MITRE ATT&CK Mapping | 2026-01-29 | 2026-01-30 | Parth , shreya , aditi | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 14 | Nmap Scan Module | 2026-01-31 | 2026-02-01 | Aditi , Shivani , Isha | Coding | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 15 | IP Reputation Module | 2026-02-02 | 2026-02-03 | Akhil, Yash , Aditi | Coding | 3- Completed | 12 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | 16 | QR / URL Scanner | 2026-02-03 | 2026-02-04 | Yash , Bhavana , Isha | Coding | 3- Completed | 10 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | 17 | AI Assistant | 2026-02-06 | 2026-02-07 | Bhavana , shreya | Coding | 3- Completed | 10 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | 18 | RAG Knowledge System | 2026-02-07 | 2026-02-08 | Shrividya, Parth , Aditi | Coding | 3- Completed | 10 | 4 | 2 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | 19 | Dockerization | 2026-02-09 | 2026-02-10 | Shivani , Parth , Shivani | Coding | 3- Completed | 10 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 20 | Nginx Configuration | 2026-02-10 | 2026-02-11 | Isha , Shivani , Parth , Yash | Coding | 3- Completed | 12 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | 21 | Role-Based Dashboard | 2026-02-11 | 2026-02-12 | Aditi , Akhil , Shrividya | Documentation | 3- Completed | 12 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | 22 | Data Optimization | 2026-02-12 | 2026-02-12 | Yash , Bhavana , Isha | Documentation | 3- Completed | 10 | 4 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | 23 | System Testing | 2026-02-12 | 2026-02-13 | Aditi , Shivani , Shrividya | Documentation | 3- Completed | 10 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | 24 | Agile Documentation | 2026-02-13 | 2026-02-13 | Yash , Shreya, Aditi | Documentation | 3- Completed | 10 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 (07-Jan) | Confusion in finalizing system architecture design | Conducted team discussion and finalized initial microservice-based structure after GitHub initialization.
Sprint 1 | Day 5 (09-Jan) | Difficulty integrating multiple threat intelligence APIs during early phase | Experimented with various APIs and tested responses on demo web visualization to evaluate feasibility.
Sprint 1 | Day 7 (11-Jan) | Inconsistent API response formats across providers | Implemented dynamic response parsing and validation logic for uniform data handling.
Sprint 2 | Day 10 (14-Jan) | API key exhaustion occurring multiple times | Optimized API usage strategy, reduced redundant calls, and implemented controlled scheduling.
Sprint 2 | Day 12 (16-Jan) | Demo dashboard showing unstable or partial threat data | Completed core features as per planned modules and stabilized feature integration.
Sprint 2 | Day 14 (18-Jan) | Structural inefficiencies identified during mentor review | Refactored backend logic, optimized architecture flow, and implemented mentor-suggested improvements.
Sprint 2 | Day 15 (19-Jan) | AbuseIPDB integration failing intermittently | Re-tested configuration multiple times and restructured request handling until stable integration achieved.
Sprint 3 | Day 18 (22-Jan) | Dashboard performance extremely slow during aggregation | Optimized database queries and reduced heavy aggregation operations.
Sprint 3 | Day 20 (24-Jan) | Over-dependency on Excel-based intermediate storage | Removed unnecessary Excel references and shifted to direct database-driven architecture.
Sprint 3 | Day 22 (26-Jan) | AlienVault OTX API architecture creating complexity and delays | Simplified system design by removing OTX-heavy architecture and restructuring data flow.
Sprint 4 | Day 25 (29-Jan) | Major performance and scalability limitations discovered | Rebuilt core program from scratch with cleaner architecture and efficient modular structure.
Sprint 4 | Day 27 (31-Jan) | Final system optimization before submission | Cleaned unused code, improved execution flow, and finalized complete working version aligned with project features.
Sprint 4 | Day 29 (02-Feb) | Documentation inconsistencies during final compilation | Standardized documentation structure and finalized Agile report.
Sprint 5 | Day 33 (06-Feb) | Version compatibility issues between backend dependencies | Aligned package versions and created a consistent requirements configuration.
Sprint 5 | Day 35 (08-Feb) | Real-time updates failing during WebSocket testing | Debugged event listeners and improved real-time broadcasting logic.
Sprint 5 | Day 37 (10-Feb) | Database indexing missing in initial schema design | Added indexing on frequently queried fields to improve performance.
Sprint 5 | Day 39 (12-Feb) | Improper error handling during API failures | Implemented centralized error handling and fallback response mechanisms.
Sprint 5 | Day 40 (13-Feb) | Team coordination delays during final restructuring phase | Conducted focused sprint meetings and redistributed tasks for faster completion.

## Retrospection
Sprint # | Sprint | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-29 | 2026-01-12 | All Team Members | Clearly defining requirements and architecture before coding | Starting development without finalizing environment setup | Daily sync meetings and collaborative planning | Finalized architecture, resolved Git conflicts, standardized environment configuration
2 | Sprint 2 | 2026-01-13 | 2026-01-26 | All Team Members | Implement structured backend modules with validation and proper schema mapping | Making API calls without rate-limit handling | Backend and API collaboration | Implemented JWT fixes, optimized MongoDB schema, added API caching and response validation
3 | Sprint 3 | 2026-01-27 | 2026-02-09 | All Team Members | Improve real-time simulation and dashboard responsiveness | Using static mock data for frontend validation | Cross-team testing during feature integration | Optimized Socket.IO broadcasting, improved simulation logic, enhanced dashboard query performance
4 | Sprint 4 | 2026-02-10 | 2026-02-23 | All Team Members | Strengthen security modules and threat validation mechanisms | Ignoring edge cases in scan validation | Code reviews before merging security features | Improved Nmap validation, enhanced MITRE mapping accuracy, secured QR scanner